## Sheet1
Transit + lead time |  | Composite Valve Block | Gate Valve | Metal Seal | Tubing Hanger | Wing Blocks |  | Time till August 1st | 166 days
Supplier 2 | Romania | 242 | 142 |  | 232 | 167 | Suppliers | Country | Lead time
Supplier 5 | France |  | 149 | 138 |  | 181 | Supplier 1 | Malaysia | 216
Supplier 7 | Brazil | 244 | 124 | 112 | 212 | 156 | Supplier 2 | Romania | 167
[7 empty] | Supplier 3 | UK | 194
[7 empty] | Supplier 4 | US | 180
[7 empty] | Supplier 5 | France | 181
[7 empty] | Supplier 6 | Poland | 190
Supplier 2 | Romania | 242 | 142 |  | 232 | 167 | Supplier 7 | Brazil | 156
[7 empty] | Supplier 8 | China | 186
[7 empty] | Supplier 9 | Italy | 181
[7 empty] | Supplier 10 | India | 213
[7 empty] | Supplier 11 | Brazil
*lead times in days

## Cost Breakdown
Poland |  | Romania |  | Brazil
Gate Valve | 2600000 | Tubing Hangar | 3482000 | Wing Block | 202000
Metal Seal | 700000 | Wing Block | 516000

## Pricing Scheme
Delivery 1 - 10 Trees |  |  |  |  | Delivery 2 - 30 Trees
Poland |  | Qty | Total Price | Unit Price |  | Qty | Total Price | Unit Price
| Gate Valve | 20 | 650000 | 32500 |  | 60 | 1950000 | 32500 | 2600000
| Metal Seal | 50 | 175000 | 3500 |  | 150 | 525000 | 3500 | 700000
Romania |  | Qty | Total Price | Unit Price |  | Qty | Total Price | Unit Price
| Tubing Hangar | 10 | 870500 | 87050 |  | 30 | 2611500 | 87050 | 3482000
| Wing Block | 0 | 0 | 8600 |  | 60 | 516000 | 8600 | 516000
Brazil |  | Qty | Total Price | Unit Price |  | Qty | Total Price | Price
| Wing Block | 20 | 202000 | 10100 |  |  |  |  | 202000
Total Delivery Cost Per Supplier |  |  |  | Discount Amount |  | Total Cost After Discounts
Poland
| 3300000 |  |  | 330000 |  | 2970000
Romania
| 3998000 |  |  | 399800 |  | 3598200
Brazil | 202000 |  |  | 0 |  | 202000
Total Project Cost
6770200

## Exhibit 0 (Schedule)
| Mobilization Schedule | [23 empty] | 153 days | 243 days | 243 days | 166 days
| COMPONENT | CRITICALITY | QTY | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  |  | Transit + lead time |  | Composite Valve Block | Gate Valve | Metal Seal | Tubing Hanger | Wing Blocks |  |  |  | Suppliers | Composite Valve Block | Gate Valve | Metal Seal | Tubing Hanger | Wing Blocks
| Composite Valve Block | 10 | QTY: 1 ea; Oct: Load Sales Order; Nov: Able to Place PO; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality; Aug: Receive; Sep: Assemble 10 Trees; Nov: Receive; Dec: Assemble 30 Trees |  |  |  | Supplier 1 | Malaysia | 254 | 152 | 145 | 256 | 216 |  |  | Malaysia | Supplier 1 | 82050 | 39000 | 3050 | 87600 | 7500 | Malaysia | Metal Seal | 610000 | 18300 | 628300
| Gate Valve | 7 | QTY: 2 ea; Nov: Engineering Activities - Part on Hold; Feb: Able to Place PO; Mar: Supplier Lead Time + Transit Time | 153 days | Gate Valve |  | Supplier 2 | Romania | 242 | 142 |  | 232 | 167 | without engineering |  | Romania | Supplier 2 | 80500 | 31000 | 0 | 87050 | 8600
| Metal Seal | 8 | QTY: 5 ea; Nov: Able to Place PO; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality | 243 days | Metal Seal |  | Supplier 3 | UK | 236 | 143 |  | 238 | 194 |  |  | UK | Supplier 3 | 88560 | 38420 | 0 | 83450 | 8880
| Tubing Hanger | 10 | QTY: 1 ea; Nov: Able to Place PO; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality | 243 days | Tubing Hangar |  | Supplier 4 | US | 278 | 126 | 118 | 223 | 180 |  |  | US | Supplier 4 | 88000 | 33600 | 4000 | 85000 | 9000
| Wing Blocks | 5 | QTY: 2 ea; Nov: Engineering Activities - Part on Hold; Feb: Able to Place PO; Mar: Supplier Lead Time + Transit Time | 166 days | Wing Blocks |  | Supplier 5 | France |  | 149 | 138 |  | 181 | with engineering |  | France | Supplier 5 | 0 | 41000 | 3900 | 0 | 8980
|  |  |  | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 |  |  |  | Supplier 6 | Poland |  | 138 | 137 |  | 190 |  |  | Poland | Supplier 6 | 0 | 32500 | 3500 | 0 | 8325
[22 empty] | Supplier 7 | Brazil | 244 | 124 | 112 | 212 | 156 | without engineering |  | Brazil | Supplier 7 | 92200 | 36800 | 3650 | 86000 | 10100
| Mobilization Schedule | [20 empty] | Supplier 8 | China | 259 | 152 | 144 | 253 | 186 |  |  | China | Supplier 8 | 74300 | 28325 | 2150 | 81200 | 8200
| COMPONENT | CRITICALITY | QTY | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  |  | Supplier 9 | Italy |  | 154 | 141 |  | 181 |  |  | Italy | Supplier 9 | 0 | 34450 | 3940 | 0 | 8700
| Composite Valve Block | 10 | QTY: 1 ea; Oct: Load Sales Order; Nov: Start 40 Comp Block; Jan: Jan 9 Comp Block Done; Apr: Receive 40 Comp Block; Aug: Receive; Sep: Assemble 10 Trees; Nov: Receive; Dec: Assemble 30 Trees |  |  |  | Supplier 10 | India |  | 155 | 153 |  | 213 |  |  | India | Supplier 10 | 0 | 25000 | 1800 | 0 | 7350
[22 empty] | Supplier 11 | Brazil | 214 | 114 |  | 212 |  |  |  | Brazil 2 | Supplier 11 | 95450 | 37400 | 0 | 86900 | 0 | bar: Feb to Jul
[20 empty] | France | Gate Valve | bar: Nov to Jul
| Tubing Hangar | 10 | QTY: 1; Nov: Order Tubing Hangar; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality; Jul: Tubing Hangar Delivered |  |  | Metal Seal
[22 empty] | Romania | buying |  | gate valve | Tubing Hangar |  |  |  |  | Gate Valve |  |  | Supplier 6 Poland |  | Gate valve maybe | bar: Feb to Jul
| days in month |  |  | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 |  | Romania | Tubing Hangar | Supplier 7 brazil |  |  | Wing block | only viable one |  |  |  |  | Metal Seal
Tubing Hangar
| Time Remaining |  | Oct: 426; Nov: 396; Dec: 365; Jan: 334 |  | Brazil | Wing Blocks | [9 empty] | Wing Blocks
| Comp Valve lead time | 70 | Nov: 40; Dec: 9; Jan: 356; Feb: 328; Mar: 297; Apr: 297
[8 empty] | Time Till Delivery | 457
[22 empty] | Gate Valve | Metal Seal | Tubing Hangar | Wing Blocks | Total Cost | Discount | [7 empty] | Gate Valve | Metal Seal | Tubing Hangar | Wing Block | Total Cost | Discount | Net Total Cost
[34 empty] | Poland | 2600000 | 2125000 |  | 2116500 | 6841500 | 1231470 | 5610030
[21 empty] | Romania | 3120000 |  | 3482000 | 688000 | 7290000 | [7 empty] | Romania | 2480000 |  | 3482000 |  | 5962000
[21 empty] | Poland | 2600000 | 700000 |  | 666000 | 3966000 | [7 empty] | Italy |  | 788000
[20 empty] | Supplier 7 | Brazil | 2944000 | 730000 | 3440000 | 808000 | 7922000
[21 empty] | Italy | 2756000 | 788000 |  | 696000 | 4240000
Transit Cost
[22 empty] | Malaysia | Metal Seal | 610000 | 18300 | 628300 |  |  |  | price | Transit Cost | discount | Total Cost |  |  |  | Price | Transit COst | discount | Total cost | Engineer | cost + eng | SPI
[28 empty] | Gate Valve | Romania | 2480000 | 49600 | 0 | 2529600 |  | Gate Valve | France | 3280000 | 65600 | 328000 | 3017600 | 100000 | 3117600 | 1.08
[28 empty] | Gate Valve | Brazil | 2944000 | 58880 | 0 | 3002880
|  |  | Jan: Supplier 2 - Romania; Apr: On Time Delivery Percentage Rate 86% |  |  | Total Quantity of Parts Required | [6 empty] | Gate Valve | Poland | 2600000 | 52000 | 0 | 2652000 |  | Tubing Hangar | Romania | 3482000 | 69640 | 348200 | 3203440
Mobilization Schedule | [29 empty] | Gate Valve | Metal Seal | Tubing Hanger | Wing Blocks |  | Gate Valve | Metal Seal | Tubing Hanger | Wing Blocks
COMPONENT | CRITICALITY | QTY | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  |  | Required Components by Deadline | Quantity | [6 empty] | Romania | 31000 | 0 | 87050 | 8600 |  | 142 |  | 232 | 167 | 153 days | Gate Valve
Composite Valve Block |  | Oct: Load Sales Order; Aug: Receive; Sep: Assemble 10 Trees; Nov: Receive; Dec: Assemble 30 Trees | [11 empty] | Poland | 32500 | 3500 | 0 | 8325 |  | 138 | 137 |  | 190 | 243 days | Metal Seal
Gate Valve |  | Nov: Engineering Activities - Part on Hold; Feb: Order Gate Valve; Mar: Lead Time + Transit TIme; Jun: June 20 - Gate Valve Delivered; Jul: Gate Valve in storage | [6 empty] | Volume Discounts |  |  |  |  | Brazil | 36800 | 3650 | 86000 | 10100 |  | 124 | 112 | 212 | 156 | 243 days | Tubing Hangar
Metal Seal | [20 empty] | Gate Valve | 80 |  | Volume Discount Spend Levels | Machining |  |  |  | Italy | 34450 | 3940 | 0 | 8700 |  | 154 | 141 |  | 181 | 166 days | Wing Blocks | bar: Nov to Jul
Tubing Hangar | 10 | QTY: 1; Nov: Order Tubing Hangar; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality; Jul: Tubing Hangar Delivered |  |  |  | Metal Seal | 200 |  | Greater than $3,000,000 | 10%
Wing Block |  | Nov: Engineering Activities - Part on Hold; Feb: Order Wing Blocks; Mar: Lead Time + Transit Time; Jul: July 17 - Wing Block Delivered |  |  |  | Tubing Hangar | 40 |  | Greater than $6,000,000 | 18%
|  |  | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 |  |  |  | Wing Blocks | 80 | [10 empty] | INCIDENTS | Quality Issue | OTD
[30 empty] | Supplier 7 - Brazil | SPI 1.19 |  | 1 | 3 | 85%
| Supplier 2 - France TTD | [28 empty] | Tubing Hangar |  | Use engineer to improve quality issues and otd
|  | QTY: Total Days; Nov: Transit TIme; Dec: Lead TIme; Jan: Criticality | [12 empty] | Wing Blocks
[31 empty] | Unit Cost | Price | Quantity |  |  | Price | Transit Cost | Discount | Net Total Cost
[30 empty] | Tubing Hangar | 86000 | 3440000 | 40 |  |  | 4344100 | 86882 | 434410 | 3996572
| Gate Valve | QTY: 142; Nov: 42; Dec: 100; Jan: 0 | [5 empty] | Transit Time and Cost | [6 empty] | Wing Blocks | 10100 | 808000 | 80 |  |  | 3440000 | 68800 | 344000 | 3164800 | just tubing hangar
| Tubing Hangar | QTY: 262; Nov: 42; Dec: 190; Jan: 30 | [5 empty] | From Region | To Manuf. Plant SAM Cost (% over Total Price) | To Manuf. Plant SAM LT, Days |  |  |  |  | Supplier 1 - Malaysia | SPI 1.2 |  | 2 | 1 | 86%
| Wing Blocks | QTY: 167; Nov: 42; Dec: 125; Jan: 0 | [5 empty] | Europe | 2% | 42 |  |  |  |  | Metal Seal |  | Cheapest option, we have long lead time on hand so extra time does not matter
[23 empty] | North America | 3% | 28
[23 empty] | South America | 2% | 14
|  | Feb: Supplier 5 - France; May: On Time Delivery Percentage Rate 89%; Sep: likely higher after using engineer | [5 empty] | Asia Pacific | 3% | 56 | [5 empty] | Unit Cost | Price | Quantity |  |  | Price | Transit Cost | Discount | Net Total Cost
Mobilization Schedule | [29 empty] | Metal Seal | 3050 | 610000 | 200 |  |  | 610000 | 18300 | 0 | 628300
COMPONENT | CRITICALITY | QTY | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Composite Valve Block | 10 | QTY: 1 ea; Oct: Load Sales Order; Nov: Able to Place PO; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality; Aug: Receive; Sep: Assemble 10 Trees; Nov: Receive; Dec: Assemble 30 Trees
Gate Valve | 7 | QTY: 2 ea; Nov: Engineering Activities - Part on Hold; Feb: Order Gate Valve; May: May 31 - Gate Valve Delivered; Jun: Gate Valve in Storage | [12 empty] | Supplier 2 - Romania | SPI 1.11 |  | 2 | 2 | 89%
Metal Seal | 8 | QTY: 5 ea; Nov: Order Metal Seal; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality; Mar: March 17 - Metal Seal Delivered; Apr: Metal Seal in storage |  |  |  | Transit + lead time | Gate Valve | [7 empty] | Gate Valve |  | Use engineer to improve otd |  | cheaper than brazil |  | also allows us to hire engineer for free because we save roughly $100,000 by using romania instead of poland | [6 empty] | Lets you play into "building up your supplier more"
Tubing Hanger | 10 | QTY: 1 ea; Nov: Able to Place PO; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality |  |  |  | Supplier 11 | 114
Wing Blocks | 5 | QTY: 2 ea; Nov: Engineering Activities - Part on Hold; Feb: Order Wing Blocks; Mar: Supplier Lead Time + Transit TIme; Aug: August 1 - Wing Blocks Delivered |  |  |  | Supplier 7 | 124
|  |  | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 |  |  |  | Supplier 4 | 126 | [8 empty] | Unit Cost | Price | Quantity |  |  | Price | Transit Cost | Discount | Net Total Cost
[21 empty] | Supplier 6 | 138 | [7 empty] | Gate Valve | 31000 | 2480000 | 80 |  |  | 2480000 | 49600 | 0 | 2529600
[21 empty] | Supplier 2 | 142
Supplier 5 - France TTD | [20 empty] | Supplier 3 | 143
| Total Days | Oct: Transit TIme; Nov: Lead TIme; Dec: Criticality |  |  |  | Supplier 5 | 149
Gate Valve | 149 | Oct: 42; Nov: 107; Dec: 0 |  |  |  | Supplier 8 | 152
Metal Seal | 168 | Oct: 42; Nov: 96; Dec: 30 |  |  |  | Supplier 1 | 152
Wing Blocks | 181 | Oct: 42; Nov: 139; Dec: 0 |  |  |  | Supplier 9 | 154 | [15 empty] | Cost of Suppliers | 7154472
[21 empty] | Supplier 10 | 155 | [15 empty] | 2 Engineer @100k | 200000
|  | Feb: Supplier 7 - Brazil | [20 empty] | Final Cost | 7354472
Mobilization Schedule | [19 empty] | Lead Time for Parts (Days)
COMPONENT | CRITICALITY | QTY | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Suppliers | Composite Valve Block | Gate Valve | Metal Seal | Tubing Hanger | Wing Blocks
Composite Valve Block | 10 | QTY: 1 ea; Oct: Load Sales Order; Nov: Able to Place PO; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality; Aug: Receive; Sep: Assemble 10 Trees; Nov: Receive; Dec: Assemble 30 Trees |  |  | Supplier 1 | 198 | 96 | 89 | 200 | 160
Gate Valve | 7 | QTY: 2 ea; Nov: Engineering Activities - Part on Hold; Feb: Able to Place PO; Mar: Supplier Lead Time + Transit Time June 5th delivery |  |  | Supplier 2 | 200 | 100 |  | 190 | 125
Metal Seal | 8 | QTY: 5 ea; Nov: Able to Place PO; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality March 21st |  |  | Supplier 3 | 194 | 101 |  | 196 | 152
Tubing Hanger | 10 | QTY: 1 ea; Nov: Able to Place PO; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality July 1st |  |  | Supplier 4 | 250 | 98 | 90 | 195 | 152
Wing Blocks | 5 | QTY: 2 ea; Nov: Engineering Activities - Part on Hold; Feb: Able to Place PO; Mar: Supplier Lead Time + Transit Time July 7th |  |  | Supplier 5 |  | 107 | 96 |  | 139
[20 empty] | Supplier 6 |  | 96 | 95 |  | 148
[20 empty] | Supplier 7 | 230 | 110 | 98 | 198 | 142
|  | Feb: Supplier 6- Poland |  |  | Supplier 8 | 203 | 96 | 88 | 197 | 130
Mobilization Schedule | [19 empty] | Supplier 9 |  | 112 | 99 |  | 139
COMPONENT | CRITICALITY | QTY | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Supplier 10 |  | 99 | 97 |  | 157
Composite Valve Block | 10 | QTY: 1 ea; Oct: Load Sales Order; Nov: Able to Place PO; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality; Aug: Receive; Sep: Assemble 10 Trees; Nov: Receive; Dec: Assemble 30 Trees |  |  | Supplier 11 | 200 | 100 |  | 198
Gate Valve | 7 | QTY: 2 ea; Nov: Engineering Activities - Part on Hold; Feb: Able to Place PO; Mar: Supplier Lead Time + Transit Time may 20
Metal Seal | 8 | QTY: 5 ea; Nov: Able to Place PO; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality march 16th
Tubing Hanger | 10 | QTY: 1 ea; Nov: Able to Place PO; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality
Wing Blocks | 5 | QTY: 2 ea; Nov: Engineering Activities - Part on Hold; Feb: Able to Place PO; Mar: Supplier Lead Time + Transit Time aug 10th
Supplier 5 - Brazil TTD
| Total Days | Oct: Transit TIme; Nov: Lead TIme; Dec: Criticality
Gate Valve | 110 | Oct: 14; Nov: 107; Dec: 0
Metal Seal | 140 | Oct: 14; Nov: 96; Dec: 30
Wing Blocks | 153 | Oct: 14; Nov: 139; Dec: 0; Feb: Supplier 9 - Italy
Mobilization Schedule
COMPONENT | CRITICALITY | QTY | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Composite Valve Block | 10 | QTY: 1 ea; Oct: Load Sales Order; Nov: Start 40 Comp Block; Jan: Jan 9 Comp Block Done; Apr: Receive 40 Comp Block; Aug: Receive; Sep: Assemble 10 Trees; Nov: Receive; Dec: Assemble 30 Trees
Gate Valve | 7 | QTY: 2 ea
Metal Seal | 8 | QTY: 5 ea; Nov: Order Metal Seal; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality; Mar: March 22nd - Metal Seal Delivered
Tubing Hangar | 10 | QTY: 1 ea; Nov: Order Tubing Hangar; Dec: Supplier Lead Time + Transit Time + 30 Days for Criticality; Jul: Tubing Hangar Delivered
Wing Blocks | 5 | QTY: 2 ea
days in month |  |  | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31
Supplier 5 - France TTD
| Total Days | Oct: Transit TIme; Nov: Lead TIme; Dec: Criticality
Gate Valve | 154 | Oct: 42; Nov: 112; Dec: 0
Metal Seal | 171 | Oct: 42; Nov: 99; Dec: 30
Wing Blocks | 181 | Oct: 42; Nov: 139; Dec: 0

## Sheet3
Transit + lead time |  | Composite Valve Block | Gate Valve | Metal Seal | Tubing Hanger | Wing Blocks
Supplier 1 | Malaysia | 254 | 152 | 145 | 256 | 216 | Supplier | Gate Valve | Metal Seal | Tubing Hangar | Wing Block
Supplier 2 | Romania | 242 | 142 |  | 232 | 167 | Poland | 138 | 137 | 0 | 190
Supplier 3 | UK | 236 | 143 |  | 238 | 194 | Romania | 142 | 0 | 232 | 167
Supplier 4 | US | 278 | 126 | 118 | 223 | 180 | Brazil | 124 | 112 | 212 | 156
Supplier 5 | France |  | 149 | 138 |  | 181
Supplier 6 | Poland |  | 138 | 137 |  | 190
Supplier 7 | Brazil | 244 | 124 | 112 | 212 | 156
Supplier 8 | China | 259 | 152 | 144 | 253 | 186
Supplier 9 | Italy |  | 154 | 141 |  | 181
Supplier 10 | India |  | 155 | 153 |  | 213
Supplier 11 | Brazil | 214 | 114 |  | 212

## Cost Calculator For Supplier
Bill of Materials for Next Generation Tree
Component | Criticality | Quantity
Composite Valve Block | 10 | 1 |  |  | France | Gate Valve
Gate Valve | 7 | 2 |  |  |  | Metal Seal
Metal Seal | 8 | 5
Tubing Hangar | 10 | 1 |  |  | Romania | Tubing Hangar
Wing Blocks | 5 | 2
[5 empty] | Brazil | Wing Blocks
September 1st 2025 - 10 Trees Needed |  |  | December 1st 2025 - 30 Trees Needed |  | Total Quantity of Parts Required |  | Makes 40 Trees
Required Components by deadline | Quantity |  | Required Components by Deadline | Quantity | Required Components by Deadline | Quantity
Composite Valve Block | 10 |  | Composite Valve Block | 30 | Composite Valve Block | 40
Gate Valve | 20 |  | Gate Valve | 60 | Gate Valve | 80
Metal Seal | 50 |  | Metal Seal | 150 | Metal Seal | 200
Tubing Hangar | 10 |  | Tubing Hangar | 30 | Tubing Hangar | 40
Wing Blocks | 20 |  | Wing Blocks | 60 | Wing Blocks | 80
Cost to manufacture 40 Composite Valve Blocks
| Mfg Cost | Additional Capacity Cost | Number of Units Required | Total Cost
Composite Valve Block | 147340 | 2000000 | 40 | 7893600
Bids
Pricing Schematics for Suppliers lower than 1.25 SPI | [8 empty] | Unit Cost for Parts | [6 empty] | Pricing Schematics for Suppliers greater than 1.25 SPI
[9 empty] | Suppliers | Composite Valve Block | Gate Valve | Metal Seal | Tubing Hanger | Wing Blocks | OTD% last 12 months
Supplier 1 - Malaysia | [8 empty] | Supplier 1 | 82050 | 39000 | 3050 | 87600 | 7500 | 86% | Supplier 3 - UK
| Cost Per Unit | Total Cost Per Part | Quantity | [5 empty] | Supplier 2 | 80500 | 31000 | 0 | 87050 | 8600 | 89% |  | Cost Per Unit | Total Cost Per Part | Quantity
Composite Valve Block | 82050 | 0 | 0 | [5 empty] | Supplier 3 | 88560 | 38420 | 0 | 83450 | 8880 | 88% | Composite Valve Block | 88560 | 885600 | 10
Gate Valve | 39000 | 0 | 0 | [5 empty] | Supplier 4 | 88000 | 33600 | 4000 | 85000 | 9000 | 86% | Gate Valve | 38420 | 768400 | 20
Metal Seal | 3050 | 610000 | 200 | [5 empty] | Supplier 5 | 0 | 41000 | 3900 | 0 | 8980 | 89% | Metal Seal | 0 | 0 | 50
Tubing Hangar | 87600 | 0 | 0 | [5 empty] | Supplier 6 | 0 | 32500 | 3500 | 0 | 8325 | 91% | Tubing Hangar | 83450 | 834500 | 10
Wing Blocks | 7500 | 0 | 0 | [5 empty] | Supplier 7 | 92200 | 36800 | 3650 | 86000 | 10100 | 85% | Wing Blocks | 8880 | 177600 | 20
|  |  |  | Total Cost |  |  |  |  | Supplier 8 | 74300 | 28325 | 2150 | 81200 | 8200 | 78% |  |  |  |  | Total Cost
|  |  |  | 610000 |  |  |  |  | Supplier 9 | 0 | 34450 | 3940 | 0 | 8700 | 94% |  |  |  |  | 2666100
[9 empty] | Supplier 10 | 0 | 25000 | 1800 | 0 | 7350 | 88%
|  |  |  | Total Cost after Discount |  |  |  |  | Supplier 11 | 95450 | 37400 | 0 | 86900 | 0 | 87% |  |  |  |  | Total Cost after Discount
| No Discounts |  |  | 610000 | [12 empty] | No Discounts
Supplier 1 Total Cost | 610000 | [7 empty] | Volume Discounts | [6 empty] | Supplier 1 Total Cost | 2666100
[9 empty] | Volume Discount Spend Levels | Machining
[8 empty] | >= | 3000000 | 10%
Supplier 2 - Romania | [7 empty] | >= | 6000000 | 18% | [5 empty] | Supplier 4 - US
| Cost Per Unit | Total Cost Per Part | Quantity | [13 empty] | Cost Per Unit | Total Cost Per Part | Quantity
Composite Valve Block | 80500 | 0 | 0 | [12 empty] | Composite Valve Block | 88000 | 880000 | 10
Gate Valve | 31000 | 0 | 0 | [12 empty] | Gate Valve | 33600 | 672000 | 20
Metal Seal | 0 | 0 | 0 | [12 empty] | Metal Seal | 4000 | 200000 | 50
Tubing Hangar | 87050 | 2611500 | 30 | [12 empty] | Tubing Hangar | 85000 | 850000 | 10
Wing Blocks | 8600 | 0 | 0 | [12 empty] | Wing Blocks | 9000 | 180000 | 20
|  |  |  | Total Cost | [15 empty] | Total Cost
|  |  |  | 2611500 | [15 empty] | 2782000
|  |  |  | Total Cost after Discount | [15 empty] | Total Cost after Discount
| No Discounts | [15 empty] | No Discounts
Supplier 2 Total Cost | 2611500 | [14 empty] | Supplier 1 Total Cost | 2782000
Supplier 6 - Poland | [15 empty] | Supplier 5 - France
| Cost Per Unit | Total Cost Per Part | Quantity | [13 empty] | Cost Per Unit | Total Cost Per Part | Quantity
Composite Valve Block | 0 | 0 | 0 | [12 empty] | Composite Valve Block | 0 | 0 | 0
Gate Valve | 32500 | 0 | 0 | [12 empty] | Gate Valve | 41000 | 2460000 | 60
Metal Seal | 3500 | 0 | 0 | [12 empty] | Metal Seal | 3900 | 585000 | 150
Tubing Hangar | 0 | 0 | 30 | [12 empty] | Tubing Hangar | 0 | 0 | 0
Wing Blocks | 8325 | 166500 | 20 | [12 empty] | Wing Blocks | 8980 | 0 | 0
|  |  |  | Total Cost | [15 empty] | Total Cost
|  |  |  | 166500 | [15 empty] | 3045000
|  |  |  | Total Cost after Discount | [15 empty] | Total Cost after Discount
| No Discounts | [15 empty] | No Discounts
Supplier 6 Total Cost | 166500 | [14 empty] | Supplier 1 Total Cost | 3045000
Supplier 7 - Brazil | [15 empty] | Supplier 8 - China
| Cost Per Unit | Total Cost Per Part | Quantity | [13 empty] | Cost Per Unit | Total Cost Per Part | Quantity
Composite Valve Block | 92200 | 0 | 0 | [12 empty] | Composite Valve Block | 74300 | 743000 | 10
Gate Valve | 36800 | 0 | 0 | [12 empty] | Gate Valve | 28325 | 566500 | 20
Metal Seal | 3650 | 0 | 0 | [12 empty] | Metal Seal | 2150 | 107500 | 50
Tubing Hangar | 86000 | 0 | 0 | [12 empty] | Tubing Hangar | 81200 | 812000 | 10
Wing Blocks | 10100 | 606000 | 60 | [12 empty] | Wing Blocks | 8200 | 164000 | 20
|  |  |  | Total Cost | [15 empty] | Total Cost
|  |  |  | 606000 | [15 empty] | 2393000
|  |  |  | Total Cost after Discount | [15 empty] | Total Cost after Discount
| No Discounts | [15 empty] | No Discounts
Supplier 7 Total Cost | 606000 | [14 empty] | Supplier 1 Total Cost | 2393000
Supplier 9 - Italy | [15 empty] | Supplier 11 - Brazil
| Cost Per Unit | Total Cost Per Part | Quantity | [13 empty] | Cost Per Unit | Total Cost Per Part | Quantity
Composite Valve Block | 0 | 0 | 0 | [12 empty] | Composite Valve Block | 95450 | 954500 | 10
Gate Valve | 34450 | 0 | 0 | [12 empty] | Gate Valve | 37400 | 748000 | 20
Metal Seal | 3940 | 197000 | 50 | [12 empty] | Metal Seal | 0 | 0 | 50
Tubing Hangar | 0 | 0 | 0 | [12 empty] | Tubing Hangar | 86900 | 869000 | 10
Wing Blocks | 8700 | 0 | 0 | [12 empty] | Wing Blocks | 0 | 0 | 20
|  |  |  | Total Cost | [15 empty] | Total Cost
|  |  |  | 197000 | [15 empty] | 2571500
|  |  |  | Total Cost after Discount | [15 empty] | Total Cost after Discount
| No Discounts | [15 empty] | No Discounts
Supplier 9 Total Cost | 197000 | [14 empty] | Supplier 1 Total Cost | 2571500
Supplier 10 - India
| Cost Per Unit | Total Cost Per Part | Quantity
Composite Valve Block | 0 | 0 | 10
Gate Valve | 25000 | 500000 | 20
Metal Seal | 1800 | 90000 | 50
Tubing Hangar | 0 | 0 | 10
Wing Blocks | 7350 | 147000 | 20
Total Cost
737000
Total Cost after Discount
No Discounts
Supplier 10 Total Cost | 737000

## Full schedule
Mobilization Schedule
COMPONENT | CRITICALITY | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Composite Valve Block: In house | 10 | Oct: Load sales orders; Nov: Able to Place PO Nov 1st; Dec: Lead Time (70) + Transit Time (14) + 30 Days for Criticality=114; Sep: Assemble 10 Trees; Nov: Receive; Dec: Assemble 30 Trees
Gate Valve: Supplier 6 (France) | 7 | Nov: Engineering Activities - Part on Hold; Feb: Able to Place PO March 1st; Mar: Supplier Lead Time (107) + Transit Time (42)
Metal Seal: Supplier 6 (France) | 8 | Nov: Able to Place PO Nov 1st; Dec: Lead Time (96) + Transit Time (42) + 30 Days for Criticality
Tubing Hanger: Supplier 2 (Romania) | 10 | Nov: Able to Place PO Nov 1st; Dec: Supplier Lead Time (190) + Transit Time (42) + 30 Days for Criticality
Wing Blocks 2: Supplier X () |  | Nov: Able to Place PO Nov 1st
Wing Blocks: Supplier 7 (Brazil) | 5 | Nov: Engineering Activities - Part on Hold; Feb: Able to Place PO Feb 15th; Mar: Supplier Lead Time (142) + Transit Time (14)

## Exhibit 2 (QSL)
Qualified Suppliers List | [7 empty] | 0.25 | 0.35 | 0.4
Supplier | Country | Category | Spend Based On Recipts (Past 3 Months) | HSE Recordable Incidents last 12 months | QN last 12 months | OTD% last 12 months | SPI | 1 Engineer | 2 Engineer | 3 Engineer
Supplier 1 | Malaysia | Machining | 2568214 | 2 | 1 | 86% | 1.2 | 0.95 | 0.85 |  |  | Suppliers need to be scalable up to 5 years, focus on high otd and low qn
Supplier 10 | India | Machining | 4586521 | 2 | 2 | 88% | 1.15 | 0.9 | 0.8
Supplier 11 | Brazil | Machining | 2563542 | 2 | 4 | 87% | 1.33 | 1.08 | 0.98
Supplier 2 | Romania | Machining | 6523521 | 2 | 2 | 89% | 1.11 | 0.86 | 0.76
Supplier 3 | UK | Machining | 1525685 | 3 | 2 | 88% | 1.46 | 1.21 | 1.11
Supplier 4 | US | Machining | 3251526 | 3 | 5 | 86% | 1.35 | 1.1 | 1
Supplier 5 | France | Machining | 1235895 | 1 | 2 | 89% | 1.33 | 1.08 | 0.98
Supplier 6 | Poland | Machining | 4245856 | 1 | 2 | 91% | 1.12 | 0.87 | 0.77 |  |  |  |  | Supplier 5 | France
Supplier 7 | Brazil | Machining | 3452685 | 1 | 3 | 85% | 1.19 | 0.94 | 0.84 |  |  |  |  | Supplier 2 | Romania
Supplier 8 | China | Machining | 2356856 | 2 | 4 | 78% | 1.38 | 1.13 | 1.03 |  |  |  |  | Supplier 6 | Poland
Supplier 9 | Italy | Machining | 2523851 | 1 | 2 | 94% | 1.17 | 0.92 | 0.82
SPI Calculator | [11 empty] | SPI Constant | 0.6
To calculate a supplier's SPI, you must enter the past 3 months aggregated spend, HSE recordable incidents for the last 12 months, QNs for the last 12 months, OTD % for the last 12 months, and the SPI will auto calculate in the red cell.
Spend Based On Recipts Past 3 Months | HSE Recordable Incidents last 12 months | HSE Points/$M | HSE Points | HSE SPI | QN last 12 months | QN Points | QN Points/$M | QN SPI | OTD% last 12 months | OTD SPI | SPI
2000000 | 1 | 4 | 8 | 0.066667 | 2 | 14 | 7 | 0.11667 | 89% | 0.036667 | 1.22

## Lead Times Supplier
Suppliers | Composite Valve Block | Suppliers | Metal Seal | Suppliers | Wing Blocks | From Region | To Manuf. Plant SAM LT, Days |  |  | Composite Valve Block | Gate Valve | Metal Seal | Tubing Hanger | Wing Blocks | Transit + lead time |  | Composite Valve Block | Gate Valve | Metal Seal | Tubing Hanger | Wing Blocks
Supplier 3 | 194 | Supplier 8 | 88 | Supplier 2 | 125 | Europe | 42 | Supplier 1 | Malaysia | 198 | 96 | 89 | 200 | 160 | Supplier 1 | Malaysia | 254 | 152 | 145 | 256 | 216
Supplier 1 | 198 | Supplier 1 | 89 | Supplier 8 | 130 | North America | 28 | Supplier 2 | Romania | 200 | 100 |  | 190 | 125 | Supplier 2 | Romania | 242 | 142 |  | 232 | 167
Supplier 2 | 200 | Supplier 4 | 90 | Supplier 5 | 139 | South America | 14 | Supplier 3 | UK | 194 | 101 |  | 196 | 152 | Supplier 3 | UK | 236 | 143 |  | 238 | 194
Supplier 11 | 200 | Supplier 6 | 95 | Supplier 9 | 139 | Asia Pacific | 56 | Supplier 4 | US | 250 | 98 | 90 | 195 | 152 | Supplier 4 | US | 278 | 126 | 118 | 223 | 180
Supplier 8 | 203 | Supplier 5 | 96 | Supplier 7 | 142 |  |  | Supplier 5 | France |  | 107 | 96 |  | 139 | Supplier 5 | France |  | 149 | 138 |  | 181
Supplier 7 | 230 | Supplier 10 | 97 | Supplier 6 | 148 |  |  | Supplier 6 | Poland |  | 96 | 95 |  | 148 | Supplier 6 | Poland |  | 138 | 137 |  | 190
Supplier 4 | 250 | Supplier 7 | 98 | Supplier 3 | 152 |  |  | Supplier 7 | Brazil | 230 | 110 | 98 | 198 | 142 | Supplier 7 | Brazil | 244 | 124 | 112 | 212 | 156
Supplier 5 |  | Supplier 9 | 99 | Supplier 4 | 152 | Supplier 5 | France | Supplier 8 | China | 203 | 96 | 88 | 197 | 130 | Supplier 8 | China | 259 | 152 | 144 | 253 | 186
Supplier 6 |  | Supplier 2 |  | Supplier 10 | 157 | Supplier 2 | Romania | Supplier 9 | Italy |  | 112 | 99 |  | 139 | Supplier 9 | Italy |  | 154 | 141 |  | 181
Supplier 9 |  | Supplier 3 |  | Supplier 1 | 160 |  |  | Supplier 10 | India |  | 99 | 97 |  | 157 | Supplier 10 | India |  | 155 | 153 |  | 213
Supplier 10 |  | Supplier 11 |  | Supplier 11 |  |  |  | Supplier 11 | Brazil | 200 | 100 |  | 198 |  | Supplier 11 | Brazil | 214 | 114 |  | 212
Suppliers | Gate Valve | Suppliers | Tubing Hanger |  | fast lead time for composite, metal, gate
Supplier 1 | 96 | Supplier 2 | 190 |  | supplier 1
Supplier 6 | 96 | Supplier 4 | 195
Supplier 8 | 96 | Supplier 3 | 196 |  | fast lead time for tubing and wing
Supplier 4 | 98 | Supplier 8 | 197 |  | supplier 2
Supplier 10 | 99 | Supplier 7 | 198
Supplier 2 | 100 | Supplier 11 | 198
Supplier 11 | 100 | Supplier 1 | 200
Supplier 3 | 101 | Supplier 5
Supplier 5 | 107 | Supplier 6
Supplier 7 | 110 | Supplier 9
Supplier 9 | 112 | Supplier 10

## Exhibit 6 (Transit Time)
Transit Time and Cost
From Region | To Manuf. Plant SAM Cost (% over Total Price) | To Manuf. Plant SAM LT, Days
Europe | 2% | 42
North America | 3% | 28
South America | 2% | 14
Asia Pacific | 3% | 56

## Exhibit 5 (Bids)
Bids
Unit Cost for Parts
Suppliers | Composite Valve Block | Gate Valve | Metal Seal | Tubing Hanger | Wing Blocks
Supplier 1 | 82050 | 39000 | 3050 | 87600 | 7500
Supplier 2 | 80500 | 31000 | 0 | 87050 | 8600
Supplier 3 | 88560 | 38420 | 0 | 83450 | 8880
Supplier 4 | 88000 | 33600 | 4000 | 85000 | 9000
Supplier 5 | 0 | 41000 | 3900 | 0 | 8980
Supplier 6 | 0 | 32500 | 3500 | 0 | 8325
Supplier 7 | 92200 | 36800 | 3650 | 86000 | 10100
Supplier 8 | 74300 | 28325 | 2150 | 81200 | 8200
Supplier 9 | 0 | 34450 | 3940 | 0 | 8700
Supplier 10 | 0 | 25000 | 1800 | 0 | 7350
Supplier 11 | 95450 | 37400 | 0 | 86900 | 0
Lead Time for Parts (Days)
Suppliers | Composite Valve Block | Gate Valve | Metal Seal | Tubing Hanger | Wing Blocks | Supplier 5 | #VALUE! | Raad
Supplier 1 | 198 | 96 | 89 | 200 | 160 | Supplier 2 | #VALUE! |  | Tubing Hangar | Wing Blocks | Raad
Supplier 2 | 200 | 100 |  | 190 | 125 | Supplier 6 | #VALUE! |  | Gate Valve | maybe metal seal
Supplier 3 | 194 | 101 |  | 196 | 152 | Supplier 7 | #VALUE!
Supplier 4 | 250 | 98 | 90 | 195 | 152
Supplier 5 |  | 107 | 96 |  | 139
Supplier 6 |  | 96 | 95 |  | 148
Supplier 7 | 230 | 110 | 98 | 198 | 142
Supplier 8 | 203 | 96 | 88 | 197 | 130
Supplier 9 |  | 112 | 99 |  | 139
Supplier 10 |  | 99 | 97 |  | 157 | Tubing hangar TTD |  | 262
Supplier 11 | 200 | 100 |  | 198
*Lead times include weekends | [5 empty] | Gate Valve TTD | 142
[6 empty] | wing block | 167
Transit Time and Cost
From Region | To Manuf. Plant SAM Cost (% over Total Price) | To Manuf. Plant SAM LT, Days
Europe | 2% | 42
North America | 3% | 28
South America | 2% | 14
Asia Pacific | 3% | 56

## Exhibit 3 (Discounts)
Volume Discounts
Volume Discount Spend Levels | Machining
Greater than $3,000,000 | 10%
Greater than $6,000,000 | 18%

## Exhibit 1 (Cost & Capacity)
Manufacturing Cost & Capacity
Machine | Machine Location | Part1 | Cost to Manufacture2 | Projected 2024 Volume3 | Current Capacity | Additional Capacity Cost4 | Aditional Capacity Units | Lead Time5
#1 | Singapore | Composite Valve Block | 147340 | 76 | 100 | 2000000 | 50 | 70 | 126 | days
#2 | South American Plant | Tubing Hanger | 145000 | 72 | 100 | 1500000 | 50 | 68
Notes
1Due to the complexity of these parts these parts can only be manufactured on designated machines.
2Direct material and labor represent 60% of the total cost of parts manufactured in house.
3Projected volume represents current demand for these machines due to pre-exisitng projects.
4Investments in additional capacity include expanding current proudction and aquiring new manufacturing process. Additional capacity will be available as soon as investment is made.
5Assume that lead time can be met as long as capacity remains.
Factor in additional capacity cost as a redundancy in case all pending purchase orders are not converted into sales
just say this we good
88404
Make/Buy
Suppliers | Composite Valve Block
Supplier 1 | 82050
Supplier 2 | 80500
Supplier 3 | 88560
Supplier 4 | 88000
Supplier 5 | 0
Supplier 6 | 0
Supplier 7 | 92200
Supplier 8 | 74300
Supplier 9 | 0
Supplier 10 | 0
Supplier 11 | 95450

## Exhibit 4 (SPI)
SPI Calculator | [11 empty] | SPI Constant | 0.6
To calculate a supplier's SPI, you must enter the past 3 months aggregated spend, HSE recordable incidents for the last 12 months, QNs for the last 12 months, OTD % for the last 12 months, and the SPI will auto calculate in the red cell.
Spend Based On Recipts Past 3 Months | HSE Recordable Incidents last 12 months | HSE Points/$M | HSE Points | HSE SPI | QN last 12 months | QN Points | QN Points/$M | QN SPI | OTD% last 12 months | OTD SPI | SPI
2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90% | 0.033333 | 1.0333

## Sheet2
Year | Category | Product | Sales | Rating
2017 | Components | Chains | 20000 | 75%
2015 | Clothing | Socks | 3700 | 22%
2017 | Clothing | Bib-Shorts | 4000 | 22%
2015 | Clothing | Shorts | 13300 | 56%
2017 | Clothing | Tights | 36000 | 100%
2015 | Components | Handlebars | 2300 | 35%
2016 | Clothing | Socks | 2300 | 28%
2016 | Components | Brakes | 3400 | 36%
2016 | Bikes | Mountain Bikes | 6300 | 40%
2017 | Components | Brakes | 5400 | 38%
2016 | Accessories | Helmets | 17000 | 90%
2016 | Accessories | Lights | 21600 | 90%
2016 | Accessories | Locks | 29800 | 90%
2016 | Components | Bottom Brackets | 1000 | 23%
2015 | Clothing | Jerseys | 6700 | 5%
2017 | Components | Bottom Brackets | 600 | 27%
2015 | Bikes | Road Bikes | 3500 | 50%
2017 | Clothing | Jerseys | 7500 | 40%
2017 | Accessories | Tires and Tubes | 63700 | 90%
2017 | Bikes | Cargo Bike | 9300 | 60%
2017 | Bikes | Mountain Bikes | 8500 | 46%
2017 | Accessories | Bike Racks | 33700 | 92%
2017 | Clothing | Caps | 600 | 15%
2015 | Bikes | Mountain Bikes | 3100 | 35%
2017 | Accessories | Pumps | 30700 | 95%
2016 | Accessories | Pumps | 16400 | 80%
2016 | Accessories | Bike Racks | 22100 | 90%
2017 | Accessories | Helmets | 34000 | 95%
2015 | Accessories | Pumps | 700 | 10%
2015 | Clothing | Tights | 3300 | 30%
2017 | Bikes | Road Bikes | 16900 | 65%
2017 | Accessories | Lights | 36700 | 90%
2015 | Accessories | Helmets | 8300 | 99%
2016 | Clothing | Bib-Shorts | 2900 | 36%
2015 | Accessories | Tires and Tubes | 8700 | 90%
2017 | Accessories | Locks | 35000 | 100%
2016 | Bikes | Road Bikes | 8300 | 46%
2016 | Components | Wheels | 16700 | 75%
2016 | Bikes | Touring Bikes | 1800 | 15%
2017 | Clothing | Socks | 3700 | 48%
2016 | Clothing | Shorts | 12000 | 66%
2015 | Accessories | Locks | 10000 | 85%
2015 | Components | Bottom Brackets | 500 | 35%
2017 | Components | Wheels | 21800 | 96%
2016 | Components | Chains | 16400 | 70%
2016 | Clothing | Caps | 400 | 20%
2015 | Clothing | Vests | 3300 | 36%
2017 | Components | Handlebars | 5000 | 35%
2016 | Components | Handlebars | 3300 | 38%
2015 | Components | Pedals | 800 | 36%
2016 | Clothing | Gloves | 15600 | 65%
2016 | Components | Pedals | 1500 | 17%
2017 | Components | Pedals | 6200 | 38%
2017 | Clothing | Gloves | 27000 | 88%
2016 | Components | Saddles | 2800 | 38%
2016 | Bikes | Cargo Bike | 6700 | 46%
2015 | Clothing | Gloves | 13300 | 50%
2016 | Accessories | Tires and Tubes | 13800 | 85%
2017 | Clothing | Vests | 2400 | 35%
2015 | Accessories | Bike Racks | 300 | 5%
2015 | Components | Saddles | 2100 | 49%
2015 | Components | Brakes | 2300 | 34%
2015 | Components | Wheels | 10000 | 66%
2015 | Bikes | Touring Bikes | 500 | 22%
2016 | Clothing | Jerseys | 3800 | 48%
2015 | Bikes | Cargo Bike | 3200 | 48%
2017 | Clothing | Shorts | 23000 | 100%
2015 | Clothing | Bib-Shorts | 700 | 28%
2015 | Accessories | Lights | 1300 | 90%
2016 | Clothing | Vests | 1300 | 25%
2016 | Clothing | Tights | 22100 | 99%
2017 | Components | Saddles | 3100 | 42%
2015 | Clothing | Caps | 500 | 50%
2017 | Bikes | Touring Bikes | 3100 | 22%
2015 | Components | Chains | 8700 | 92%